# Project Progress Report

Learning Management System

# Project Information

| Project Title | Learning Management System (LMS) |
| --- | --- |
| Team Leader | [Add team leader name] |
| Team Members | [Add team member names] |
| Start Date | [Add actual start date] |
| Target End Date | [Add target end date] |
| Report Date | May 2, 2026 |

# Executive Summary

The Learning Management System is approximately 86% complete. Core user-facing workflows are implemented, including the landing page, authentication and recovery screens, dashboard navigation, course management, course content, assignments, quizzes, submissions, calendar, task tracking, notifications, and student progress tracking. Recent progress includes a dedicated progress tab for students and teachers, API support through /api/progress, and a full notification interface with global state, read/unread handling, filtering, and backend event helpers. Remaining work is focused on final notification event integration, full end-to-end testing, screenshot evidence collection, bug fixing, and deployment verification.

# Module Progress Overview

| Module / Feature | Assigned To | Status | % Complete | Start Date | Target Finish | Actual Finish | Delay | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Landing Page and Branding | Project Team | Done | 100% | Feb 22 | Mar 2 | Mar 2 | 0 | Public landing page, branding assets, and responsive presentation completed. |
| Authentication and Recovery | Project Team | Done | 100% | Feb 25 | Mar 20 | Mar 20 | 0 | Login, signup, OTP recovery, password reset, and auth guard are implemented. |
| Dashboard Shell | Project Team | Done | 95% | Mar 2 | Mar 27 | Apr 1 | 5 | Main dashboard, sidebar, header stats, settings, and theme-aware layout are in place. |
| Course Management | Project Team | Ongoing | 90% | Mar 10 | Apr 10 | - | +5 | Course listing, creation/edit UI, enrollment flow, and course API are implemented; final workflow QA remains. |
| Course Content, Assignments, and Quizzes | Project Team | Ongoing | 85% | Mar 20 | Apr 18 | - | +7 | Modules, assignments, quizzes, composer, and edit modals are present; end-to-end validation remains. |
| Submissions and Grading | Project Team | Ongoing | 80% | Mar 25 | Apr 20 | - | +6 | Submission API and grading route exist; needs integrated grading notification test. |
| Student Progress Tracking | Project Team | Done | 90% | Apr 18 | Apr 28 | Apr 28 | 0 | Progress API, student view, teacher student selector, and Progress tab are implemented. |
| Notifications System | Project Team | Ongoing | 85% | Apr 21 | May 3 | - | +2 | UI, context, utilities, and API are ready; remaining task is wiring event calls into related endpoints. |
| Calendar and Tasks | Project Team | Ongoing | 80% | Mar 27 | Apr 25 | - | +4 | Calendar and tasks screens/API are routed; workflow testing and polish remain. |
| Testing and Deployment | Project Team | Ongoing | 70% | Apr 1 | May 10 | - | 0 | Vitest test files, Vite build setup, Vercel workflow, and deployment guide exist; final QA pending. |

# Module Evidence (Screenshots)

Evidence cards are filled from the current repository. Replace the right-side placeholders with actual UI screenshots after final browser testing.

| Module: Landing Page and Branding Assigned To: Project Team Status: Done (100%) Target Finish Date: Mar 2 Description: Provides the public entry point with hero, feature, process, about, testimonials, and footer sections. Remarks: Public landing page, branding assets, and responsive presentation completed. | Screenshot / Evidence Source: src/components/Hero.jsx, Features.jsx, HowItWorks.jsx, About.jsx, Testimonials.jsx, Footer.jsx |
| --- | --- |

| Module: Authentication and Recovery Assigned To: Project Team Status: Done (100%) Target Finish Date: Mar 20 Description: Handles account creation, login, protected routing, OTP email flow, and password reset. Remarks: Login, signup, OTP recovery, password reset, and auth guard are implemented. | Screenshot / Evidence Source: src/components/Login.jsx, SignUp.jsx, RecoverEmail.jsx, RecoverVerify.jsx, RecoverReset.jsx, PasswordReset.jsx |
| --- | --- |

| Module: Dashboard Shell Assigned To: Project Team Status: Done (95%) Target Finish Date: Mar 27 Description: Provides the authenticated workspace, navigation, dashboard cards, stats, and application layout. Remarks: Main dashboard, sidebar, header stats, settings, and theme-aware layout are in place. | Screenshot / Evidence Source: src/components/dashboard/dashboard.jsx, sidebar.jsx, Home.jsx, HeaderStats.jsx, Settings.jsx |
| --- | --- |

| Module: Course Management Assigned To: Project Team Status: Ongoing (90%) Target Finish Date: Apr 10 Description: Allows users to create, view, manage, and enroll in courses. Remarks: Course listing, creation/edit UI, enrollment flow, and course API are implemented; final workflow QA remains. | Screenshot / Evidence Source: src/components/courses/*, src/components/dashboard/Courses.jsx, EnrollPage.jsx, api/courses.js |
| --- | --- |

| Module: Course Content, Assignments, and Quizzes Assigned To: Project Team Status: Ongoing (85%) Target Finish Date: Apr 18 Description: Supports course detail pages, learning modules, assignments, quizzes, and quiz authoring tools. Remarks: Modules, assignments, quizzes, composer, and edit modals are present; end-to-end validation remains. | Screenshot / Evidence Source: CourseDetails.jsx, CourseTabs.jsx, QuizComposer.jsx, api/course-modules.js, api/course-assignments.js, api/course-quizzes.js |
| --- | --- |

| Module: Submissions and Grading Assigned To: Project Team Status: Ongoing (80%) Target Finish Date: Apr 20 Description: Handles assignment submissions and teacher grading workflows. Remarks: Submission API and grading route exist; needs integrated grading notification test. | Screenshot / Evidence Source: api/submissions.js and PATCH /api/submissions/:submissionId route in api-server.js |
| --- | --- |

# Module Evidence (Screenshots) - Continued

| Module: Student Progress Tracking Assigned To: Project Team Status: Done (90%) Target Finish Date: Apr 28 Description: Displays completion percentage, assignment and quiz scores, pending work, overdue work, and last activity. Remarks: Progress API, student view, teacher student selector, and Progress tab are implemented. | Screenshot / Evidence Source: PROGRESS_TRACKING.md, StudentProgress.jsx, TeacherStudentProgress.jsx, api/progress.js |
| --- | --- |

| Module: Notifications System Assigned To: Project Team Status: Ongoing (85%) Target Finish Date: May 3 Description: Provides notification bell, unread badge, full notifications page, filtering, mark-read/delete actions, and event helpers. Remarks: UI, context, utilities, and API are ready; remaining task is wiring event calls into related endpoints. | Screenshot / Evidence Source: IMPLEMENTATION-SUMMARY.md, NotificationPanel.jsx, Notifications.jsx, NotificationContext.jsx, api/notifications.js |
| --- | --- |

| Module: Calendar and Tasks Assigned To: Project Team Status: Ongoing (80%) Target Finish Date: Apr 25 Description: Supports schedule viewing and personal task tracking within the dashboard. Remarks: Calendar and tasks screens/API are routed; workflow testing and polish remain. | Screenshot / Evidence Source: Calendar.jsx, Tasks.jsx, TodoWidget.jsx, api/calendar.js, api/tasks.js |
| --- | --- |

| Module: Testing and Deployment Assigned To: Project Team Status: Ongoing (70%) Target Finish Date: May 10 Description: Covers unit/integration tests, production build, preview, and Vercel deployment preparation. Remarks: Vitest test files, Vite build setup, Vercel workflow, and deployment guide exist; final QA pending. | Screenshot / Evidence Source: tests/*.jsx, package.json scripts, DEPLOYMENT.md, .github/workflows/vercel-deploy.yml |
| --- | --- |

# Next Steps (Target by Next Week)

| 1 | Complete backend notification event integration in assignments, quizzes, submissions, and optional course modules. |
| --- | --- |
| 2 | Run full system testing for authentication, course workflows, quizzes, submissions, notifications, calendar, tasks, and progress tracking. |
| 3 | Capture and insert final screenshots for every major module in the evidence section. |
| 4 | Fix UI/API defects found during testing and verify responsive behavior on mobile and desktop. |
| 5 | Prepare final deployment on Vercel and confirm environment variables, database access, and API routing. |

Prepared from the project template PDF and repository files in C:\lms-landing. Fields in brackets should be updated with official team information.